## Cover
Cheesecoins Protocol — Arbitrum Grant Disbursement Schedule
Working draft — May 7, 2026
How to use this workbook:
1. Open the Disbursements sheet. Yellow cells are inputs you can change.
2. Adjust per-milestone bucket allocations until the totals work for you.
3. The Tranche Total column and grand totals at the bottom auto-recalculate.
4. The Repayment sheet shows the repayment-trigger logic — adjustable separately.
5. The Summary sheet auto-rolls bucket totals and percentages.
When you're done, the final numbers get folded into the grant doc sections 6 and 7.
Bucket meanings:
- Promo: paid acquisition campaigns + partner incentive payments at thresholds
- Liquidity: CURD/USDC seed on Uniswap V3 0.05% stablecoin tier
- Founder dev: solo founder time on protocol contracts + integration
- Ops: multi-keeper infra, uptime, support — monthly stipend equivalent
- Contractor: external contractor capacity for FxPegged audit prep / multi-keeper infra
- Audit: Arbitrum Audit Program contingency + final attestation gas
- CME: CME data licensing seed + first paid integration test

## Milestones
# | Milestone | Target date | Trigger (on-chain verifiable)
M1 | 5 partners across 2+ tiers | 2026-06-01 | 5 setMerchantWithTier events on MerchantRegistry (likely already onboarded by M0 — fires immediately)
M0 | Grant accepted, promo campaign launches | 2026-07-01 | Grant agreement signed; promo spend begins (Greg starts onboarding partners independently in May 2026)
M2 | CME data agreement signed; integration test live on Sepolia | 2026-07-01 | Signed CME agreement + on-chain price update events on CommodityPriceOracle
M3 | 15 partners across 3+ tiers, CURD/USDC pool live | 2026-08-01 | 15 MerchantStatusChanged events + Uniswap V3 0.05% stablecoin pool deploy tx
M4 | First Commerce NFT project fully sold out | 2026-08-01 | All scenes in a partner Commerce NFT project hit SCENE_MAX_SUPPLY cap (REPAYMENT TRIGGER)
M5 | FxPeggedRedemption module audited and deployed to mainnet | 2026-08-01 | Audit report published + module configured on FiatRedemptionVault proxy
M6 | 30 partners across all 5 tiers | 2026-12-01 | 30 MerchantStatusChanged events covering all 5 Tier enum values
M7 | Nubians North NFT project 50% sellout | 2027-03-01 | mintedPerScene cumulative >= 50% of TOTAL_MAX_SUPPLY (25,000 of 50,000) — REPAYMENT TRIGGER

## Disbursements
Milestone | Target date | Promo | Liquidity | Founder dev | Ops | Contractor | Audit | CME | Tranche total | Cumulative
M0 |  | 50000 | 0 | 3000 | 2000 | 0 | 0 | 0
M1 |  | 20000 | 0 | 3000 | 2000 | 0 | 0 | 0
M2 |  | 0 | 0 | 3000 | 2000 | 0 | 0 | 8000
M3 |  | 10000 | 20000 | 3000 | 2000 | 0 | 0 | 0
M5 |  | 0 | 0 | 3000 | 2000 | 6000 | 6000 | 0
M6 |  | 0 | 0 | 3000 | 2000 | 0 | 0 | 0
Total
Target | [8 empty] | 150000
Variance

## Summary
Bucket | Amount | % of grant | Release gate
Promo |  |  | Tranched at M0 / M1 / M2 — front-loaded
Liquidity |  |  | M2: CURD/USDC pool seed on Uniswap V3 0.05% stablecoin tier
Founder dev |  |  | $3k per milestone × 6 milestones — milestone-tied not time-tied
Ops |  |  | $2k per milestone × 6 milestones — multi-keeper infra, uptime, support
Contractor |  |  | M3: external contractor capacity against FxPegged prep
Audit |  |  | M6: contingency + final attestation; layers with Arbitrum Audit Program
CME |  |  | M7: CME data licensing seed + first paid integration test
Total

## Repayment
Cheesecoins -> Arbitrum DAO repayment schedule
Repayment begins on the EARLIER of (a) or (b) below.
Parameter | Value | Notes
Grant amount | 150000 | Total ask, mirrors Disbursements grand total
Repayment cap multiple | 1.5 | 1.5x = $225k cumulative repayment maximum
Repayment cap (USD) |  | Auto-calc: grant amount * cap multiple
Time cap (months) | 36 | From M2 (CME integration live)
Subscription rev-share % | 5% | 5% of subscription revenue from Settlement Index consumers
Commerce NFT fee % (existing) | 5% | Already deployed in ProjectSale
Trigger (a): First Commerce NFT sold out | M4 | Smaller / earlier signal — partner project fully sold
Trigger (b): Nubians North 50% sellout | M7 | Flagship collection at 25,000 of 50,000 minted
Trigger (c): Subscription rev share | M2 | When Settlement Index integration goes live
NFT-route repayment % of fees | 100% | % of protocol's 5% commerce fees that route to repayment escrow until cap is hit
Mechanism
Path A (NFT-route): when M4 (50% sellout of any Commerce NFT project) hits, the protocol's 5% commerce fee on subsequent NFT sales routes to a repayment escrow until the cap is hit. Off-chain accounting initially; can move to on-chain enforcement later.
Path B (subscription-route): from M7 onward, 5% of Settlement Index subscription revenue from consumer protocols accrues to the Arbitrum DAO treasury until the cap is hit, or 36 months from M7 (whichever first).
After cap is met, share drops to 0%. After cap is met OR 36 months from M7 (whichever first), obligation is fully satisfied.